## Slide 1: systems analysis
Planning and Scheduling

## Slide 2: Topics
Planning
  The importance of planning
  Types of planning
  Terminology
Charts
  Gantt charts
    Gantter
  CPM charts
  PERT charts
Agile planning
Analysis paralysis

## Slide 3: The Importance of Planning
Measure twice. Cut once.
Think before you act.
Do it right!
  Right product for the clients that is validated to meet the client’s needs
  Right software that is verified to conform to a specified design, satisfies a stated set of requirements, and does not have defects
  Right project management with enough process to organize the work, but not so much process that it gets in the way

## Slide 4: Types of Planning
Release planning is used to plan the project as a whole. Common release planning techniques include Gantt charts and release plans.
Iteration planning is a technique that involves designing and developing the tasks that will be completed in a certain iteration of the project. Common iteration planning techniques include PERT charts, CPM charts, and iteration plans.
Risk planning involves preparing for risks in order to avoid negative repercussions in both creation and support of the product.

## Slide 5: Terminology
Term | Definition
Task | A small, manageable step of a project that must be completed; everything in a project can be broken down into tasks
Role | A duty that a person takes on or plays in some relation to the product, such as programmer, tester, designer, client, or product manager
Work product | An output produced by a task or process
Work breakdown structure | A breakdown of a project into smaller components, usually specified hierarchically
Schedule | Tasks of a project that are mapped to a timeline
Milestone | An internal checkpoint used to measure progress (not time based, but event or action based)
Dependency | A situation where one task can’t be completed before another task is completed, or at least partially completed

## Slide 6: Work Breakdown Structure (WBS)
A project management and systems engineering technique
A deliverable-oriented breakdown of a project into smaller components
The Project Management Body of Knowledge defines the WBS as a “a hierarchical decomposition of the total scope of work to be carried out by the project team to accomplish the project objectives and create the required deliverables.”

## Slide 7: WBS Example
Image extracted from “Systems Engineering Fundamentals.” Defense Acquisition University Press, 2001

## Slide 8: Gantt Charts
Gantt charts are simple tools for visualizing project plans or schedules.
They are a kind of cascading horizontal bar chart.
Gantt charts can also be used to visualize task dependencies, the length of tasks, and deadlines.
Gantt charts are useful in both Waterfall and Agile projects.

## Slide 9: Gantt Charts (continued)
Gantt charts plot tasks on the left-hand side of the chart against dates, which are displayed at the top of the chart.
Each task is listed separately, one by one, and given its own horizontal bar.
The first scheduled task is at the top of the chart, and progressive tasks are displayed underneath it.
Each task’s bar represents the duration of that task from its start date to its finish date.

## Slide 10: Template of a Gantt Chart
Below is a rough template of what a Gantt chart looks like. In a real example, the tasks would be given descriptive names, and there would probably be several more tasks.

## Slide 11: Using Gantt Charts in Agile Projects
In order to use Gantt charts successfully with Agile methods:
  Additional context should be provided to tasks (such as identifying if there are task dependencies).
  Parts of the chart can be sectioned off as sprints.
  The charts must be used with an understanding of flexibility and adaptation to project needs (in other words, the chart could change as the project unfolds).

## Slide 12: Gantter
Web-based project scheduling
https://gantter.com
Gantter is a little quirky; be patient if you use it! 

## Slide 13: Using Google Sheets for Gantt Charts

## Slide 14: Creating Critical Path Method (CPM) Charts
Break down the tasks
Add time estimates
Determine dependencies
Create a path

## Slide 15: CPM Chart Steps 1-3
Tasks are broken down with time estimates in the little green boxes; dependencies are noted

## Slide 16: CPM Chart Step 4
Create paths
The critical path is the longest duration path of tasks between logical points.

## Slide 17: Program Evaluation and Review Technique (PERT) Chart
Similar to CPM charts, PERT charts are visual representations of a project and its tasks and dependencies.
PERT charts use nodes and edges in their graphical depictions.

## Slide 18: Agile Planning

## Slide 19: Agile Estimating
Planning poker?!
https://youtu.be/MrIZMuvjTws
https://www.planningpoker.com

## Slide 20: Analysis Paralysis
Don’t get stuck spending too much time eliciting requirements, analyzing requirements, documenting requirements, planning, creating planning charts.
The term analysis paralysis is used to refer to a problem where a software development team gets stalled trying to do a compete job of analyzing requirements, leading to stagnation of the project.

## Slide 21: Summary
In this module, we talked about:
  Planning
    Types of plans
    Charts used in planning
      Gantt charts
      CPM charts
      PERT charts
  Avoiding the evil analysis paralysis problem!